**STATE OF WISCONSIN**

**DEPARTMENT OF TRANSPORTATION**

**BUREAU OF AERONAUTICS**

**DETERMINATION OF LIQUIDATED DAMAGES FOR CALENDAR DAY CONTRACTS**

AIRPORT: (airport name)

PROJECT NUMBER: (aip/sap#)

CONTRACT NUMBER: (contract#)

CONTRACTOR: (name of contractor)

DESCRIPTION OF WORK IN CONTRACT: (describe contract work here)

|  |
| --- |
| CALCULATION FOR CONTRACT TIME AUTHORIZED: |
|  |  |  |
| a. | Days in contract (DC) | (contract days) |
| b. | Changed by C.O. (C.O.s (cos) | (+ no.) |
| c. | Time extension granted (Dates approved (dates) | (change) |
| d. | Proportionate increase per section 80-07 |  |
|  | FC\* (FC amount)OC\* (OC amount)x DC\* (DC) | (increase) |
|  | Total time authorized | (total time) |
|  |
| CALCULATION FOR LIQUIDATED DAMAGES: |
|  |  |  |
| a. | Date construction began | (begin date) |
| b. | Date construction completed | (completed date) |
| c. | Days to complete construction | (days to complete) |
| d. | Total time authorized | (total time) |
|  | Difference | (difference) |
|  |  |
| LIQUIDATED DAMAGES AT $(per diem) x (# of days) days = | $(damages) |

PREPARED BY: Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

\*FC - Final Cost exclusive of additional work for which additional time was granted.

\*OC - Original Contract cost

\*DC - Days in Contract (days in contract)

(initials)

574dev.dot/r.05/03/13